## Cover
Approved by | Position | Date | Signature
Doc. Ref | Version | Classification | Doc. Author
Secret
Reviewed By | Date | Signature | Doc. Owner | Date | Signature
Version | Date | Revision Author | Summary of Changes

## Risk Register
Risk ID | Risk Description | Impact | Related Asset | Risk Owner | Risk Treatment Implementor | Controls | Probability | Impact | Risk Rate | Risk Level | Risk Treatment Methodolgy | ISO 27001 Control | Response Plan | Status | Implementation Date | Probabilty | Impact | Risk Rate | Risk Review | Result of Monitoring | Evidences
1 | Cable Damage or Cut in Physical Layer causing loss of connectivity | Network downtime and data transmission failure | Network cables, switches, and physical infrastructure. | Network Infrastructure Manager. | Network Infrastructure Team Lead | Use cable management, protective conduits, and regular inspections. | 3 | 5 | 15 |  | Mitigate | A.11.1.4 Protecting Equipment. | Inspect physical infrastructure regularly/ Quickly replace or repair damaged cables. | Implemented |  | 1 | 3 | 3 | Quarterly physical audits | Low Risk (Monitoring) | Physical audit reports and repair logs
2 | Attacker spoofs MAC addresses to bypass security controls. | Unauthorized access to network segments | Switches, network interface cards (NICs) | Network Security Administrator | Network Security Engineer | Enable port security on switches and use MAC filtering | 3 | 3 | 9 |  | Mitigate | A.13.1.1 Network Controls | Configure port security to limit allowed MAC addresses / Monitor network for suspicious MAC activity. | Partially Implemented |  | 1 | 1 | 1 | Monthly network security audits | Low Risk (Monitoring) | Switch logs; security audit reports
3 | Use of outdated or weak encryption algorithms exposing data. | Data confidentiality breach. | Encryption software, communication channels. | IT Security Manager. | Security Architect / System Admin | Upgrade to strong encryption standards (e.g., TLS 1.3) | 2 | 5 | 10 |  | Mitigate | A.10.1.1 Cryptographic Controls | Audit encryption methods used/ Replace weak algorithms with strong, updated ones. | Implemented |  | 0 | 3 | 0 | Quarterly encryption assessments | Low Risk (Monitoring) | Encryption audit reports; configuration files | 0
4 | Attacker forges IP addresses to gain unauthorized access or disrupt communication. | Unauthorized access, network disruption. | Routers, firewalls, IP address management systems | Network Operations Manager | Network Security Engineer | Implement ingress and egress filtering on routers | 1 | 3 | 3 |  | Mitigate | A.13.1.1 Network Controls | Configure routers to drop packets with invalid IP addresses/ Audit router configurations regularly | Implemented |  | 0 | 1 | 0 | Quarterly router audits | Low Risk (Monitoring) | Router logs; audit reports
5 | Flooding target with TCP connection requests to exhaust resources | Service disruption or denial of service | Network servers and firewalls | Security Operations Center (SOC) Manager | SOC Team / Network Security Engineer | Deploy DoS mitigation tools and configure rate limiting. | 5 | 5 | 25 |  | Mitigate | A.13.1.3 Protection Against Malicious Code | Monitor network traffic for abnormal spikes/ Activate DoS mitigation appliances | Implemented |  | 2 | 3 | 6 | Weekly traffic analysis during peak hours | Low Risk (Monitoring) | Traffic monitoring reports; incident logs.
6 | Unauthorized user takes over a valid session. | Data theft or unauthorized actions | Session management systems, web servers | Application Security Lead | Application Security Lead / DevOps | Use encrypted session tokens and implement session timeouts. | 3 | 5 | 15 |  | Mitigate | A.10.1 Cryptographic Controls. | Enforce use of HTTPS and secure cookies/ Monitor session activities for anomalies | Implemented |  | 1 | 3 | 3 | Monthly session security reviews. | Low Risk (Monitoring) | Security logs; vulnerability scans
7 | Injection of malicious SQL queries to manipulate databases | Data loss, unauthorized data access | Database servers, web applications | Application Development Manager | App Development Lead | Implement input validation and parameterized queries | 4 | 4 | 16 |  | Mitigate | A.14.2 Security in Development and Support Processes. | Conduct secure coding training | Ongoing |  | 2 | 2 | 4 | Bi-monthly application security testing | Low Risk (Monitoring) | Penetration test reports; code review logs